## Sheet1
date | issue | status | notes
2016-08-16 | Audio not working | Resolved
2016-08-16 | Check interval | Pending
2016-08-16 | Add new audio and loops | Pending
2016-08-16 | Add interactive keyboard | Resolved | need to clean up piano keys a little
2016-08-16 | mp3 not playing or not simultaneous | Pending | FILE FORMAT ISSUE. Must figure out how to convert mp3 into ima4 to save CPU space on iOS
2016-08-16 | clone chords above melody to mark below melody | Resolved
2016-08-16 | allow individual columns to calibrate based on note and note key | Resolved | draft58
2016-08-16 | Allow notes to change while playing loop | Pending
2016-08-17 | chords should be an octave lowerr than the melody | Resolved
2016-08-20 | last and secondLast classes not playing notes | Resolved
2016-08-21 | clean up the keyboard | Pending
2016-08-22 | Piano keys should change the column | Resolved
2016-08-22 | Split black piano keys into sharp and flat | Resolved | could use labels
2016-08-22 | Bassline should be the bottom of each chord | Resolved
2016-08-22 | notes need to change for top 2 rows | Resolved
2016-08-22 | Remove low-register buttons | Resolved
2016-08-22 | Remove sharps and flats during calibration | Resolved
2016-08-26 | Notes stay sharp or flat at calibration | Resolved
2016-08-26 | New chord - melody + bass chord + up one third | Resolved | not sure if it's right